Internal Audit Update Report for the Audit Committee November 2019

This document has been prepared for the Audit Committee to provide a status update in relation to the actions arising from Internal Audit Inspections.

The current register includes 43 recommendations; over three-quarters of which have been issued since February this year.

Of the 43 recommendations 22 have been identified as complete by the Force; as these have to be signed off by the auditors they remain on the action plan as “Closed locally awaiting sign off” until this is fulfilled.

The remaining live actions continue to be monitored, with regular updates provided by their owners.

The action plan below provides details of the ‘live’ actions with status updates from the action owners.

It should be noted that the RAG (Red, Amber and Green) rating descriptors have been amended to reflect the completion status of the recommendation. The colour key can be found at the end of the report.

Gill Currie

HMIC Liaison Officer

Cleveland Police

[Type the abstract of the document here. The abstract is typically a short summary of the contents of the document. Type the abstract of the document here. The abstract is typically a short summary of the contents of the document.]

Item 11

| No | Ref | Action Owner | Audit Finding | Implementation Date |  | Agreed Management Action | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Original | Revised |  |  |
| 280 | ICS 2017 | Ken Russell (Operational Security Manager) | Microsoft withdrew support for their Windows Server 2003 and Windows XP operating systems in 2014 and 2015 respectively, from which time bug fixes and new vulnerabilities are no longer being addressed. Review of the Force’s server infrastructure during the audit identified six servers using the out of date Windows 2003 operating system, and seven machines running Windows XP Recommendation ICT management to ensure that the out of support servers and machines are decommissioned and replaced and services migrated as soon as practical. Where this is not possible management should ensure risk acceptance has been documented. (Priority 2) | Q2 2018 | Q4 2019 | Contact: Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk Action Owner – Ken Russell - left in March 2019 Delivery Manager – as above Report Published September 2017 Presented to Audit Committee 14/12/17 Cleveland have 6 XP desktop systems, 5 of which have a solution in progress. The remaining XP system requires the replacement of a specialist scanner which requires budget approval from the force. Each system is isolated from the network in terms of Internet and email access. Cleveland have 3 Windows 2003 servers, 2 are due to be decommissioned as part of two projects being progressed. The third Server to be decommissioned by the end of Q2 2018 due to business planning and budget constraints. A security plan is to be devised to ensure that this system is further locked down as much as possible to limit network exposure. ICT are meeting with the business in October to accelerate this process. Meeting 16th November JG and GC Action remains on-going and is within the implementation timeframe. 05/12/2017 Ken Russell All remaining networked XP systems have been decommissioned. A single XP system required for SOCO, still remains but has been rendered standalone, with no technical capacity for network or internet access, including email. Of the 3 Windows 2003 Servers, 1 has now been decommissioned with one in progress as per CSH Project plans , plans are now progressing to decommission this server before December Change freeze - 17/12/2017. This leaves the final server already planned to be decommissioned in Q2 2018. ## Update: 23/02/2018 A single XP system remains. Due to be decommissioned by end of June 2018 This is due to plans in place to upgrade the dependant applications and software compatible with Windows 10. Several attempts to migrate the XP solution to a virtual platform have failed due to compatibility issues. Compass 7 upgrade to Compass 8 will allow a Windows 10 migration. A single Windows 2003 server remains. Due to be decommissioned by end of December 2018 This is due to the dependency of i-Vet vetting solution. I-Vet is due to be replaced in Q4 this year, until then the current solution is required which is dependant of MS 2003 Server architecture. See report above re Risk and Mitigation. Update May 2018 A single Windows 2003 Server still exists in order to support I-Vet. The Cleveland vetting application. This is due to be replaced by Core Vet, and due to current CSH workloads, will complete by end of June 2018. Software is still to be purchased and impacted for implementation and ongoing support. Update September 2018 The single Windows 2003 remains in service. However, CoreVet will commence implementation in November to replace i-Vet, to allow the decommissioning of the Windows 2003 Server. Expect this to complete by mid-December 2018. November 2018 Detailed explanation provided to the Audit Committee members in relation to the risk of having just one server and how the data is being protected. March 2019 We still have a remaining Windows Server 2003 in place solely to provide support for i-vet. Access and the scope of server functionality has been limited to ensure only the vetting staff and ICT admin staff have only the access required, with protective monitoring in place to further safeguard access controls in place. ICT and Maria Laden are progressing Core Vet, which replaces i-Vet. This is scheduled to complete by 31/03/2019. This work will see the decommissioning of the Windows Server 2003 (also in March), as the new vetting system goes live. A very recent update by ICT confirms the project work remains on track. Update September 2019 As per action 345 decommissioning of I-Vet was delayed due to a back record conversion issue moving data into the new Core-Vet system. The decommissioning completion due date is 4th October 2019. Update October 2019 Decommissioning remains outstanding. Although I-Vet and supporting systems have been removed the audits that track people accessing the folders are still on the server and need to be rehomed/removed. This is in progress and will be concluded in November 2019. |  |
| 312 | FOI2018 | Maria Laden Data Protection Manager | A report entitled Police Systems Auditing and Administration was provided by the Data Protection Manager. Review of this document revealed that a number of systems have not been audited and that this is an issue which needs to be addressed prior to the implementation of GDPR. Recommendation It be ensured that audits of systems are carried out in a timely manner prior to the implementation of GDPR. (Priority 2) | 01/05/18 | 31/12/19 | Contact: Action Owner – Maria Laden Maria.laden@cleveland.pnn.police.uk 01642 306881 Delivery Manager – as above Report Published April 2018 Presented to Audit Committee 24/5/18 Management Comment There is a work flow audit on-going in readiness for the introduction of GDPR, I support the comments made as many of the systems used and which contain personal data are not audited either on an on-going basis or indeed at all. A stipulation of GDPR is the requirement for Data Controllers to evidence their compliance with the Regulation; this requires the need for continual auditing of both systems and workflows. I will be requesting that an additional auditing post is created to complete this task. Update September 2018 The information management team is currently going through a restructure which includes the introduction of an Auditor role. Once the restructure is approved recruitment will commence. The Auditor will assist me (DPM) in getting the force GDPR compliant and once we are they will continue to audit it to ensure we maintain compliance, this includes systems. Update March 2019 The new role for DPA/GDPR Auditor has been agreed and is currently out for advert. I expect the post to be filled by late April 2019 when a comprehensive auditing regime will be set up. Update August 2019 The GDPR Auditor commenced her role 24th June and is currently setting up an auditing regime for across the Force. Her training on PND and CAID is now complete and system auditing will commence imminently. |  |
| 313 | FOI2018 | Maria Laden Data Protection Manager | The Data Protection Disclosure Officer revealed that there is no-one to cover his duties should he be absent from work. Recommendation It be ensured that there is another officer appropriately trained on processing Subject Access Requests who could cover the Data Protection Disclosure Officer's duties in the event of his absence. (Priority 3) | 01/05/18 | 31/12/19 | Contact: Action Owner – Maria Laden Maria.laden@cleveland.pnn.police.uk 01642 306881 Delivery Manager – as above Report Published April 2018 Presented to Audit Committee 24/5/18 Management Comment A business case will be taken to Towards 2020 to gain agreement on the use of the individual on a permanent basis, along with a further review on the unit to reduce the issue of single points of failure. Update September 2018 This action is also part of the restructure. FOI and Information rights will be merged for resilience. A Business Apprentice will be appointed to assist with the admin until we have had a chance to see the long term impact of GDPR as additional resources may be required if intake increases further. Update March 2019 Once the FOI and Information Rights team have merged resilience to both areas will be introduced. In addition the Force has agreed to fund an admin apprentice post in this area, the post is currently out for advert with Middlesbrough LA. Updated August 2019 Merging of FOI and Information Rights has not progressed due to the disparity in pay grades. The Information Rights Officer is to be regraded and an Apprentice role has been developed to assist this area of the business as its work load has increased considerably since GDPR went live. The apprenticeship will last for 1 year at which point a permanent full time Information Right Officer Post will be requested. |  |
| 318 | LW2018 | Head of People and Development | At the present time Lone Working is an integral part of risk assessments that are managed by the Specialist Support and Planning Unit (Operations and Emergency Planning Manager). They do not have corporate control and the risk is that some Officers / staff members who have not been risk assessed may be involved in ‘Lone Working’ without having received any instruction or training. It would therefore be an enhanced control feature to have a more corporate approach to ‘Lone Working’ with HR taking a more informed approach to monitor Lone Working arrangements. Recommendation Human Resources to have a corporate responsibility for Lone Working and to monitor the Lone Working arrangements. (Priority 2) | 31/3/19 | 30/12/19 | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published November 2018 Presented to Audit Committee 28/2/19 Management Comment Agree HR to develop short policy statement and link to risk assessment process. N.B. just lone working not to include Agile Working. Update October 2019 The draft Lone Working policy has completed force-wide consultation (29/10), the policy is now being reviewed against the issues raised and will be presented to the People and Wellbeing Board on 18th November. Following approval there it will be presented to the Executive Management Board for approval at their first available meeting and be made live (expected December). In conjunction with the People service admin team, we are in the process of designing arrangements whereby we can monitor those who are lone working and dip sample to check the arrangements in place are appropriate and adequate. |  |
| 319 | LW2018 | Head of People and Development | As ‘Lone Working’ is not a recognised specific discipline at this time it is not identified as such in diaries or other documents. That said it was apparent that ‘Lone Working’ is adequately covered within the overall risk assessment. The risk here is that many of the staff/Officers did not understand the term ‘Lone Worker’ and as such staff/Officers who have not been risk assessed may find themselves in a ‘Lone Working’ situation without the relevant training or knowledge to deal with any potential threat. Recommendation All staff/Officers be made aware of what ‘Lone Working’ is and the requirement to be Risk Assessed if they believe they may be now, or at some future time, Lone Working.(Priority 3) | 31/3/19 | 30/12/19 | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published November 2018 Presented to Audit Committee 28/2/19 Management Comment Link action 1 in regards to communication. Update September 2019 As soon as the policy is approved by executive management board we will publish a piece in the brief promoting the policy and the importance of process. HR Business Partners will also ensure that the importance of lone working safety is discussed in management teams. The need to consider and abide by the process has now been included in induction checklists. A reminder has been added to both employee and manager information whenever an individual moves role or location. |  |
| 320 | LW2018 | Wellbeing Manager | ‘Lone working’ is not a specific health and safety matter that is used as a driver for lone working activities. Indeed several of the Officers contacted regarding ‘Lone Working’ had never heard of the phrase and were not sure what was meant by it. It is, however, clear that it is an integral part of a Police Officers activities and would be included as part of their personal training plan. As such risk assessments are undertaken for all operational staff/officers that would include all known ‘Lone Workers’ and these assessments are managed by the Operations and Emergency Planning Manager. The specific personal risk assessments cover the planned activities for the Officer and this includes ‘Lone Working’. However, there is not a separate specific list of risk assessments that relate specifically to ‘Lone Working’. While this is not an issue and ‘Lone Working’ is included in personal risk assessments, there is no overarching awareness of ‘Lone Working. Indeed, HR do not have any involvement with ‘Lone Working’. It would be good practice as part of the wellbeing initiative to include Lone Working as an integral part of this initiative. Recommendation HR to include Lone Working as part of the wellbeing initiative.(Priority 3) | 31/3/19 | 31/12/19 | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published November 2018 Presented to Audit Committee 28/2/19 Management Comment Included in the wellbeing strategy and delivery plan. Update September 2019 Lone working will include the wellbeing initiative by : Information on the wellbeing site regarding lone working and will include the link to the policy. Also as part of the wellbeing communication strategy there will be an input developed around lone working, around looking after yourself when lone working and also as a supervisor of lone workers. This communication will be repeated 6 monthly. |  |
| 321 | LW2018 | Head of People and Development | It would be good practice to raise the profile and awareness of ‘Lone Working’ within the Force for both Officers and staff. This should be done by having the Lone Worker HSE guidelines clearly present on the Force’s intranet. This was actioned during the audit visit. In addition, there is a Lone Workers NCALT e-learning package available via the intranet and all “lone workers” should be encouraged to use this training facility. Recommendation Human Resources to follow up on the raising awareness initiative and to obtain evidence that Lone Working is fully understood by Officers and staff.(Priority 3) | 1/11/18 | 31/12/19 | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published November 2018 Presented to Audit Committee 28/2/19 Management Comment HR Business Partners to include Lone Working as a regular agenda item for the HR and Wellbeing performance management pack for review on a quarterly basis. Update September 2019 Lone working will be a topic for discussion at HR and ER clinics in addition to command management teams. Also see 319 above. HR Business Partners will dip sample via telephone interview the arrangements in place for those who work alone. |  |
| 322 | LW2018 | Dave Moir Head of Specialist Support and Planning Unit | ‘Lone Working’ is an important area for the Force and should be appropriately managed, monitored and controlled. Regular reporting on these should also be made to an appropriate Board to identify trends and to make sure the risks flowing from these areas of activity are adequately controlled, reported upon and appropriate action taken to prevent or reduce the risks in future. Recommendation A reporting framework which enables Lone Working to be regularly monitored and reported to an appropriate Board within the Force be adopted.(Priority 3) | 31/3/19 | 31/12/19 | Contact: Action Owner – Dave Moir Dave.Moir@cleveland.pnn.police.uk 01642 302850 Delivery Manager – Dave Moir Report Published November 2018 Presented to Audit Committee 28/2/19 Management Comment This can be reported twice a year at the risk and governance board. Update March 2019 The actions given to SSPU were addressed by establishing a link with NCALT covering lone working e-learning material and the uploading of lone working HSE guidance documentation on our SharePoint. This was publicised via Corporate Communications in The Brief (as recorded on the TIAA Action Plan Review dated 11/2018). The auditor agreed with me at that time that this is an HR issue and not one sitting with SSPU. I pointed out then that given the prevalence for single crewed working amongst Officers and the wide range of Police, PCSO, CSI, PSI, police staff etc. activities there are hundreds individual examples of lone working each week across the Force. This is addressed by exception within risk assessments where there is an identified element of an elevated hazard e.g. Police Staff Investigators conducting interviews in the community without having access to a baton, cuffs, incapacitant etc. or CSIs being left alone at a scene to gather forensic evidence. Update September 2019 Subject to confirmation of the Force structure this will be included as a standing item on H&S agendas when we re-instate the Command H&S meetings in line with the Force H&S Policy; akin to: - Local Policing North - Local Policing South - CDSOU These will take place on a quarterly basis under the Chair of the respective C/Superintendents or in the case of CDSOU the Head of Command. The Injury on Duty Report will also be amended to incorporate a box asking the IP to indicate if they were lone working at the time of their injury and if this was a contributory factor in order to identify trends and reduce further risks. |  |
| 323 | KFC 2018 | G Gallagher | Testing identified that the supporting documentation for two credit notes was not as expected. Both credits notes were correctly applied. Recommendation Credit notes be only raised on receipt of correct documentation. (Priority 3) | Complete |  | Contact: Action Owner – Gerard Gallagher Gerard.Gallagher@cleveland.pnn.police.uk 01642 301234 Delivery Manager – Gerard Gallagher Report Published November 2018 Presented to Audit Committee 28/2/19 Management Comment Comment noted: Process updated to accommodate request. Update March 2019 Processes in place, action completed. |  |
| 324 | HRR19 | Head of People Services | During the sample testing undertaken during the audit it was noted that these documents did not hold a date or any version control reference. Without such information there is a risk that incorrect job descriptions and person specifications may be used by departments or issued to potential applicants. Recommendation Job Description and Person Specification documentation be dated and version controlled. (Priority 2) | Complete |  | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment Change the job description/person spec to have an element of version control. Currently in progress and Could be implement with effect from 1st March 2019. Update September 2019 A new template for police staff person specifications and job descriptions has been devised which now date stamps each page and this links to the version control section located at the back of each job description/person specification. This information does not change. This was introduced in July 2019. However, due to the vast increase to Police Officer Recruitment in addition to a temporary reduction to resource within the Recruitment Team, it has not been absolutely maintained. Now that the team is fully resourced and some additionality has been approved, all police staff roles advertised will be on the new template. Action Complete |  |
| 325 | HRR19 | Head of People Services | The documentation audit trail for interview scoring and outcomes was found to be incomplete in some of the sample tested. Recommendation A review of the process for the receipt of interview records and outcomes be undertaken to ensure that all required documentation is returned to People Services form the Hiring Manager/Interviewer(s). (Priority 2) | 4/4/20 |  | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment A review will take place into this action during the next financial year. Update September 2019 A new interview record process has been devised which affords a hiring manager 3 attempts to return the required paperwork over a 3 week window to the HR team. On the 3rd request – the Head of Service is cc’d into the email in an attempt to return required information. This was implemented in July 2019. However, due to the vast increase to Police Officer Recruitment in addition to a temporary reduction to resource within the Recruitment Team, it has not been absolutely maintained. Now that the team is fully resourced and some additionality has been approved, all police staff roles advertised, will follow the revised process. |  |
| 326 | DMS19 | Head of People Services | The Annual Leave Policy (Policy Ref: 216) is currently at Version 2.5 having being reviewed in March 2014 and due for review in October 2018. It was noted that there was a version change in June 2018, however, the full review of the policy is now overdue. Recommendation In accordance with the recommended review date, which was October 2018, the review of the Annual Leave Policy 216 be undertaken at the earliest opportunity. (Priority 3) | 1/2/20 |  | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment Noted Update October 2019 In order to ‘future proof’ the Annual Leave Policy a further period of consultation has been undertaken in relation to the introduction of the Workforce Optimisation Unit’ early next year. Consultation ended on 21st October and the policy will continue through the approval process until it is signed off at the first available Executive Management Board – expected December. |  |
| 327 | DMS19 | Head of People Services | Attendance Management - (Policy103) - This policy was last reviewed in June 2018 and is due for review every two years. However, at section 3.22.5 it states "There is at November 2017 a review of the force Annual leave policy on-going then this may impact on the information provided above." It is misleading if matters need to be addressed in the document but the impression is that a full review has been undertaken which has moved forward the next review date by two years. Recommendation When a review of a Policy document is undertaken this is for the whole document. Should minor amendments be required between reviews this be noted in the version control section of the document. (Priority 3) | Complete |  | Contact: Action Owner – ACO Brian Thomas Brian.thomas@cleveland.pnn.police.uk 01642 301700 Delivery Manager – People Services Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment Noted – The new Policy is in the stage of a ‘soft launch’ with the Force in order to collate feedback and will go live within the next two weeks. Update October 2019 All policies (and guidance documents) contain a version control section at the end of the document where details of all reviews and updates are recorded. Where there has been a minor amendment the paragraph number is also noted along with the details of the change, to help the reader quickly identify what has changed. Policies have set review dates but are updated every time a change happens or a process change is required irrespective of when the review is due. This process was already in place. Action closed. |  |
| 328 | P2019 | Payroll Business Partner Bev Cook | Testing of new starter payroll data identified that whilst evidence was seen in each file to support the audit trail for the inputter as well as for the independent check by another member of the Payroll team, it was noted that this was not always on the same document in each file and sometimes on several documents. It was agreed with the Payroll Business Partner that a format for holding the new starter documentation in the employee file would be introduced and that the stamp/initials would be applied to the Contractual Details Form as a standard practice. Recommendation The format for holding new starter documentation in an employee file be agreed with the input/review stamp being applied to the Contractual Details Form in all cases. (Priority 3) | Complete |  | Contact: Action Owner – Bev Cook Beverley.cook@cleveland.pnn.police.uk 01642 301234 Delivery Manager – Bev Cook Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment Comment noted and agreed. Update March 2019 Processes in place, action completed. |  |
| 329 | SARC19 | Commissioner’s Officer for Victims | Specific Contract Terms - The contract has some specific Conditions precedent that must be met by the Provider. It is noted that a number of the Conditions Precedent within the Contract have not yet been met. These either require progressing or recorded as work in progress so that these are not overlooked. Recommendation The Conditions Precedent in the contract be progressed and either marked as completed or work in progress. For those in progress these be monitored. (Priority 2) | Complete |  | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment The Conditions Precedent have been provided to the co-ordinating commissioner (NHS England). Items to be marked as complete following the next Contract and Performance Meeting. Update March 2019 Quarterly contract and performance meetings taking place. Action recommended for closure |  |
| 330 | SARC19 | Commissioner’s Officer for Victims | The quality initiatives are excellent and demonstrate that the team are focused on the needs and benefits of the recipient of the service. Now that many of those output based measures have been identified the team should look to create a template for these and for this template report to form a regular submission to the monitoring group meetings. Reports are currently provided to the Contract and Performance Group meetings in terms of adherence to the quality requirements. Recommendation A template be created of the output performance measures and be reported to every monitoring group meeting. (Priority 3) | Complete |  | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment This information is routinely reported to the quarterly Contract and Performance Meetings as part of the service provider’s performance reports. A number of the quality measures are only relevant to the SARC service or the ISVA service and not both. Update March 2019 A Quality Framework is in place that providers are required to submit on a quarterly basis. In addition to this the provider is required to provide a SARC Indicators of Performance Document which includes output performance measures. This is a national requirement for SARCs across the Country. Examples of the mentioned documents are available and are discussed in detail at quarterly contract and performance meetings. Action recommended for closure |  |
| 331 | SARC19 | Commissioner’s Officer for Victims | Also within the contract is a section entitled Schedule 4 Quality Requirements, which lists a number of local quality requirements. These should form a reporting mechanism for the Provider which can then be reviewed by the Contract and Performance Group as part of their regular monitoring arrangements as above this information in reported to the C&P meetings. Recommendation The Quality Requirements listed in the contract be reviewed and regularly reported to the Contract and Performance Group. (Priority 3) | Complete |  | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment As above Update March 2019 As detailed in number 330 above. Action recommended for closure |  |
| 332 | SARC19 | Commissioner’s Officer for Victims | With regard to the Teesside SARC ISVA NE Crisis worker agreement it would be good practice to review and confirm that the stated requirements under this contract have either been actioned, are work in progress or are no longer applicable as these would have been key requirements for the Provider to comply with as part of the tendered submission. Recommendation The stated requirements under the contract be reviewed and it be confirmed that they have been either actioned, are work in progress or no longer applicable. (Priority 3) | Complete |  | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment OPCC and NHS to jointly review the stated requirements to determine whether applicable or otherwise. Update March 2019 This was discussed at the contract and performance meeting held on 19 March and will be actioned by NHS England. Action no longer applicable to the force – recommended for closure |  |
| 333 | SARC19 | Commissioner’s Officer for Victims | Following award of contract the commissioning team have produced a corporate risk register for the service. While the register contains a number of key concerns that are being monitored and reported upon there is no clear link with whether the issues identified are having a detrimental impact on the core delivery of the service. Consideration should be given to relating risks to service delivery and whether any of these risks could have a significant impact upon the successful delivery of the contract. Recommendation Risks be related to service delivery and it be determined if any of those risks have a significant impact upon the successful delivery of the contract. Appropriate action be considered / taken for any risks with a significant impact. (Priority 3) | 12/02/2019 | End December 2019 | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment For discussion at the next Contract and Performance Meeting where both NHS England and the service providers are in attendance. Update March 2019 The provider follows NHS England guidelines in terms of the recording and monitoring of risks and issues. (Awaiting further information of the guidance document from NHS England). Training for providers around what a risk is and what an issue is being considered to ensure the correct information is being actioned. Update September 2019 At the quarter 1 contract and performance meeting the provider presented a new format risk and issues log based on the guidance provided by NHS England. This has ensured that only risks are included on the risk register with issues (something that has already happened and therefore no longer a risk) being recorded separately. This has given the risk register a greater focus on risks that impact upon service delivery. This new format will be reviewed moving forward at the quarterly contract and performance meetings. |  |
| 334 | SARC19 | Commissioner’s Officer for Victims | It will prove challenging to assess whether value for money is being achieved and whether the outcomes are able to be demonstrated as cost effective. This is clearly work in progress for the team and with appropriate monitoring and management of the service in the course of time a fair view can be taken as to what the service should cost and what the outcomes and benefits are. The financial management should therefore be closely monitored and a relationship developed between cost and outcomes Recommendation To enable a view to be taken with regard to value for money financial management be closely monitored and a relationship developed between cost and outcomes. (Priority 3) | 1/4/2019 | End December 2019 | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment The contract is still in the very early stages of delivery. A greater understanding of the true cost of the service will be obtained in time allowing for costs v outcome to be considered. However, given the type of service this is, it is difficult to predict demand and outcomes can vary depending on the individual. Deep dive on the services finances will take place at the end of year 1 of the service which is 31 March 2019. Update March 2019 No update at this stage. As above finances will be reviewed once the service has delivered for a full 12 month period. Update September 2019 The first 12 months of service delivery has allowed commissioners to gain a greater understanding of demand and costs associated with delivery of a SARC service. This is information that we didn’t previously have available to us due to historic funding arrangements. Due to this commissioners are still working through the budget in detail to ensure that a quality service is being delivered within the financial envelope provided. One of the things which has become apparent during year 1 is in terms of the difficulty in maintaining people on zero hours contracts for out of hours SARC cover. This has provided a risk in terms of a lack of 24/7 cover should the SARC be required out of hours. NHS England have therefore awarded the provider some additional funding to look at a different more sustainable way of working. It is envisaged the new proposed way of working will provide greater value for money and a quality service to victims including mitigating the risk of availability outside of office hours. |  |
| 335 | SARC19 | Commissioners Office for Victims, Crime and Justice, Operational Crime Team | Given the uncertainty of the initial service provision with the issue of staffing and who might transfer under TuPE and the unknown quantity as to victim participation it would be good practice in conjunction with the Provider to review the service and the various costs involved, say after the first year of operation. Also such items as the provision and maintenance of major capital items need to be clarified. Recommendation The client to take responsibility for the capital assets (these can be those items with an expected life of more than one year) while the Provider to take responsibility for maintaining those items. (Priority 3) | Complete |  | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment The OPCC will maintain responsibility for the capital assets used by the police i.e. Police Achieving Best Evidence (ABE) Equipment and Video Link Facilities. These are to be included on the Cleveland Police Capital Replacement Plan moving forward. Update March 2019 Work is on-going around SARC assets. Update September 2019 Cleveland, Durham, Northumbria and Cumbria OPCCs and NHS England have recently released a prior information to inform the market that consideration is being given to the joint procurement exercise for SARC services to commence 1 April 2021. A North East and Cumbria SARC Project Team to manage this procurement has been established and we are working through arrangements such as these to ensure clarity for potential providers moving forward. This will require agreement from all organisations involved in the procurement. Action complete. |  |
| 336 | SARC19 | Commissioner’s Officer for Victims | The Provider has pointed out that the relationship is not balanced with the Teesside element of the contract being more under their control. For Durham and Northumbria, who do not contribute financially to this contract, they have staff within their Police establishment who provide part of the SARC service. This undoubtedly causes tension that the Provider is attempting to manage. In going forward, this arrangement should be reviewed to support the continuing success of the project. Recommendation Every effort be made to consider co-commissioning opportunities with Northumbria and Durham going forward to align SARC management across the region. (Priority 3) | Complete |  | Contact: Action Owner – PCC Delivery Manager – Rachelle Kipling Rachelle.kipling@cleveland.pnn.police.uk 01642 301208 Report Published February 2019 Presented to Audit Committee 28/2/19 Management Comment Durham, Northumbria and North Yorkshire are all named within the current contract so could join if they wish. A meeting is scheduled for 13 February 2019 with Durham and Northumbria to discuss opportunities for co-commissioning. Update March 2019 A North East SARC Project Team has been established involving a representative from each of the three PCC Offices and NHS England. The Team meet on a regular basis to discuss future collaboration opportunities. Action recommended for closure |  |
| 337 | SC2019 | Operational Support Manager | A detailed review of the guidance document was carried out and it was identified that a number of processes had changed in the previous year, some of which came about due to the above issue. The process maps do not, therefore, reflect the current procedures being operated. Recommendation All procedures/process maps be reviewed to ensure that they reflect the processes that have now been agreed and adopted. (Priority 2) | Complete |  | Contact: Action Owner – Chief Finance Officer Delivery Manager – Sandra Swan Sandra.swan@cleveland.pnn.police.uk 01642 301285 Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Recommendation accepted-Procedures and process maps to be updated to reflect the revised system for seized cash. Update August 2019 All process maps have been updated and reviewed and are now confirmed as fit for purpose. Action recommended for closure |  |
| 338 | SC2019 | Operational Support Manager | The matters identified at the three safes visited during the audit assignment were similar to the issues that were raised in last year's audit of seized cash. The continued occurrence of insufficient data being recorded on Niche, items being incorrectly recorded or the tardiness of updating the safe log book compromises the integrity of the system operated and could lead to losses being incurred by the Force. Recommendation Niche users who book in items be periodically reminded of the minimum requirements for entries onto Niche, details required on cash bags and the processes for updating the safe log books when items are placed in or removed from the safe. (Priority 2) | Complete |  | Contact: Action Owner – Chief Finance Officer Delivery Manager – Sandra Swan Sandra.swan@cleveland.pnn.police.uk 01642 301285 Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Recommendation accepted- Safes to be removed from Hartlepool and Stockton. Safes at Middlesbrough subject to new controls and all correspondence with users of safes to be through Niche. Message to all to be circulated regarding seized cash procedures. Update August 2019 Following further consultation, the safes remain at Stockton and Hartlepool and the safe at Kirkleatham reinstated. Revised procedures have been written and implemented and are being monitored monthly. Local Inspectors have been tasked with monitoring the entries into Niche and training to be organised for Officers if required. The new system has been confirmed with Internal Audit. Action recommended for closure |  |
| 339 | SC2019 | Strategic Finance Manager | The matters identified at the three safes visited during the audit assignment were similar to the issues that were raised in last year's audit of seized cash. The continued occurrence of insufficient data being recorded on Niche, items being incorrectly recorded or the tardiness of updating the safe log book compromises the integrity of the system operated and could lead to losses being incurred by the Force. Recommendation A monthly sample check of items held in the inspectors' safes be undertaken to monitor compliance with the required processes and highlight where discrepancies are identified. (Priority 2) | Complete |  | Contact: Action Owner – Chief Finance Officer Delivery Manager – Sandra Swan Sandra.swan@cleveland.pnn.police.uk 01642 301285 Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Recommendation accepted. Monthly check of Safes to be conducted. Update August 2019 Monthly checks of safes being conducted by Central Cash Team and errors have been reducing. Action recommended for closure |  |
| 340 | SC2019 | Operational Support Manager | A sample of 42 of the 107 items were held in the cash team safes was selected for review. The following matters were noted: - Six items in the sample were found to have no comments recorded on Niche; - Three items were recorded on Niche as 'other' instead of 'cash'; - One bag was not sealed; - One bag included a non-cash item (Biro Pen); and - One bag held sterling as well as foreign currency, which should have been split. Recommendation Items received for the main cash team safes be checked when being received and not entered until the correct information has been provided. (Priority 2) | Complete |  | Contact: Action Owner – Chief Finance Officer Delivery Manager – Sandra Swan Sandra.swan@cleveland.pnn.police.uk 01642 301285 Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Recommendation accepted. Changes to seized cash system proposed with one seized cash safe and 2 holding safes operating. Items not to be placed in the seized cash safe until all information received and correctly recorded. Update August 2019 A new system has been introduced and accepted by Internal Audit. Items not correctly entered into Niche are remaining in the local safe until correctly completed and any issues with the bagging of cash is being raised as a work request though Niche so it can be escalated to higher ranking Officers if required. Monthly safe audits being conducted by Central Cash team and errors corrected by individuals as required. Action recommended for closure |  |
| 341 | SC2019 | Strategic Finance Manager | Interest figures are provided by the Treasury team in a gross format. To assist in clarity the figure provided should clearly show the seized cash element, interest element and the total required to repay. Recommendation Interest figures provided by the Treasury team be clear and show the seized cash element, interest element and the total required to repay (Priority 1) | Complete |  | Contact: Action Owner – Chief Finance Officer Delivery Manager – Sandra Swan Sandra.swan@cleveland.pnn.police.uk 01642 301285 Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Recommendation accepted and already implemented. |  |
| 342 | ICTF2019 | Network Manager Vineesh Viswanath | Password complexity requirements are not enforced by the firewall systems. Recommendation ICT to ensure all firewall administrator accounts use complex passwords and that these are stored in the password management system. (Priority 2) | Complete |  | Contact: Action Owner – Vineesh Viswanath Vineesh.viswanath@cleveland.pnn.police.uk 01642 301187 Delivery Manager – as above Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Firewall policy updated to enforce complex password with 90 days expiry. Update September 2019 As stated above, complex password introduced, action closed. |  |
| 343 | ICTF2019 | Service/Operations Manager Paul Stocks | Regular reviews of firewall rulesets should be introduced. Recommendation ICT to introduce a yearly documented review of firewall rulesets on completion of the rationalisation exercise to ensure the validity of all rules. (Priority 2) | 01/04/19 | 01/04/20 | Contact: Action Owner – Paul Stocks Paul.stocks@cleveland.pnn.police.uk 01642 301277 Delivery Manager – as above Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Calendar entry created to plan annual review as required. Update October 2019 The review of firewall rulesets has been added to the ICT Audit Schedule to be completed quarterly. The first review took place in late October; the results will determine the frequency of reviews; dependent upon whether any issues are found. |  |
| 344 | ICTNS2019 | Head of ICT | The Network Security Policy and Force Information Security Policy require review and updating to reflect current requirements and controls. Recommendation ICT policies should be reviewed and updated on an annual basis and/ or as a result of significant changes to processes and procedures. (Priority 2) | Complete |  | Contact: Action Owner – Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk 01642 301864 Delivery Manager – as above Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Network Security Policy – the issue date on the title page is misleading. The document history states Dec 2018, this is confirmed by the last modified date on SharePoint as 7th Dec 2018. Information Security Policy – the draft provided was reviewed and approved shortly after the audit by Phil Brook ISO. |  |
| 345 | ICTNS2019 | David Wain | The out of support Windows 2003 operating system is still use to support the i-Vet application. Recommendation Decommission the remaining out of support 2003 Windows server on completion of the i-Vet system migration. (Priority 2) | 31st May 2019 | November 2019 | Contact: Action Owner – Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk 01642 301864 Delivery Manager – David Wain Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Decommissioning of I-Vet has been delayed due to a back record conversion issue moving data into the new system called Core-Vet. Update October 2019 Decommissioning completion expected November 2019 |  |
| 346 | ICTNS2019 | Network Manager Vineesh Viswanath | There is not currently a documented process in place detailing the approach to the patching of network managed devices including routers, switches and firewalls. Recommendation Patch process documentation and patching schedules for network devices should be created. (Priority 2) | Complete |  | Contact: Action Owner – Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk 01642 301864 Delivery Manager – Vin Viswanath Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Documenting a process is in progress. The method has been piloted at Hartlepool Police Station on the 16th April. Update September 2019 Security Patch Policy updated to include Network devices. Action Complete |  |
| 347 | ICTNS2019 | Vin Viswanath / Martin Metcalf | At the time of audit the Log Rhythm tool was unavailable due to technical issues. Recommendation Ensure the Log Rhythm access issue is investigated and resolved. (Priority 3) | Complete |  | Contact: Action Owner – Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk 01642 301864 Delivery Manager – Vin Viswanath / Martin Metcalf Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment This is currently still outstanding, target date for resolution is 10th May 2019. Update September 2019 Issue with Log Rhythm service resolved. Action complete |  |
| 348 | ICTNS2019 | Head of ICT | It was noted during the audit that Information Asset Owners have been assigned to key Force information assets, but that ICT were in the process of ensuring all assets have been identified, in particular network shares and mailbox accounts. A significant exercise was in the process of being completed at the time of audit to identify these assets. Recommendation Ensure all network shares/ mailboxes are identified and that Information Asset Owners are appropriately assigned. (Priority 3) | Complete |  | Contact: Action Owner – Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk 01642 301864 Delivery Manager – as above Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment Owners and automated monthly update checking has been in place for a number of years, sample provided in the evidence pack. |  |
| 349 | ICTNS2019 | Ian Taylor | The potentially insecure ‘Telnet’ service was found to be present on the Force’s domain controller server. Recommendation The Telnet service should be removed from the domain controller server. (Priority 3) | Complete |  | Contact: Action Owner – Oliver Plumpton oliver.plumpton@cleveland.pnn.police.uk 01642 301864 Delivery Manager – Ian Taylor Report Published April 2019 Presented to Audit Committee 23/5/19 Management Comment This was removed at the time of the audit. |  |
| 350 | CG2019 | Strategic Contracts & Governance Manager | The OPCC has a Commissioning Strategy that was produced in January 2015. This document is still a "draft for consultation" and needs to be approved and issued as a final document, although the OPCC are aware that this document needs updating which is currently work in progress. Recommendation The Commissioning Strategy and the other documents identified within the Strategy require be updated and approved as final documents. (Priority 3) | 31/03/20 |  | Contact: Action Owner – Michael Porter Michael.porter@cleveland.pnn.police.uk 01642 301291 Delivery Manager – Michael Porter Report Published April 2019 Presented to Audit Committee Management Comment The existing commissioning strategy is undergoing a complete review with the OPCC team, and will be completed by year end. Update September 2019 The OPCC team continue to assess and evaluate the business needs for 2020 onwards as part of an existing commissioning workshop. Once those plans are finalised, a commissioning strategy document will be produced and published. This work will be completed in line with the year-end timescales previously projected. |  |
| 351 | DD2019 | Head of Information/Data Protection Officer | In looking at the wider picture of digital data throughout the Force, it would benefit from a corporate application that provides a corporate and robust management system that would have review, retain and deletion capability. Recommendation The Force to review a corporate software solution, to manage across the Force, the review, retention and deletion of digital data. (Priority 3) | Capital Bid to be prepared in Q3 2019/20 for inclusion in the 2020/21 capital plan following a full business case review. |  | Contact: Action Owner – Maria Laden Maria.laden@cleveland.pnn.police.uk 01642 306881 Delivery Manager – as above Report Published August 2019 Presented to Audit Committee Management Comment The Head of Information Management/Data Protection Officer will be submitting an application for an electronic solution to unstructured data. The solution will be implemented in 2020/2021 if the bid is successful. |  |
| 352 | DQ2019 | ACC Graham (SIRO) | The Head of Information Management and Data Protection Officer stated that she has sought the agreement of the Executive Team to an Information Asset Owner Board. The remit of the Board will be to assure the Chief Constable, as Data Controller, that information asset owners are accountable for all matters relating to the Data Protection Act 2018. Research showed that the Information Asset Owner Board had only met once on 20 July 2018 with no plans for a further meeting. Recommendation The Information Asset Owner Board be re-established with a clear mandate of responsibility for information governance, clear terms of reference and regular meetings arranged. (Priority 2) | 22/10/19 |  | Contact: Action Owner – ACC Graham Delivery Manager – as above Report Published September 2019 Presented to Audit Committee Management Comment The IAO Board will recommence on 22nd October 2019. ToR will be agreed prior to this date. The acting SIRO ACC Graham will be attending as Chair. Update October 2019 The IAO Board took place on the 22nd October 2019. The ToR agreed in July 2018 were reiterated and agreed at the meeting. Two presentations have been produced and sent out to all IAOs with a covering letter from the SIRO. These are on A) GDPR Audits – what they are to include and B) Data Protection Act 2018 and the role of the IAO. The IAO Board will now sit quarterly. |  |
| 353 | DQ2019 | ACC Graham (SIRO) | Information Asset Owners (IAOs) are responsible for the management and security of paper information and electronic data that is processed, handled, stored, disseminated (information sharing) and destroyed by their respective business areas. These will generally be Heads of Service throughout the Force. Research identified that due to the many people changes over the last few months it is now unclear as to who the Information Asset Owners are within the Force. Recommendation Information Asset Owners be clearly identified, their responsibility for information management clearly defined and an up to date list maintained corporately. (Priority 2) | 22/10/19 |  | Contact: Action Owner – ACC Graham Delivery Manager – as above Report Published September 2019 Presented to Audit Committee Management Comment IAOs have been identified and agreed by Exec, these are the Officers/staff who will be attending the meeting on 22nd October 2019 Update October 2019 IAOs attended the meeting on 22nd October 2019. The Board re-issued the cabinet office guidance (May 2018, Version 1.3) on the Guidance of the Role of the IAO. All IAOs will follow this guidance. |  |
| 354 | DQ2019 | Head of DSE | In reviewing a number of Data Quality / Information Governance policies it was noted that some proof reading was required to update where staff had left and to correct some minor inconsistencies Recommendation The various policies and procedures relating to Data Quality/Information Governance be proof read and updated. (Priority 3) | 30/11/19 |  | Contact: Action Owner – Cristiana Emsley Cristiana.emsley@cleveland.pnn.police.uk 01642 302212 Delivery Manager – as above Report Published September 2019 Presented to Audit Committee Management Comment Ongoing. |  |
| 355 | DQ2019 | Head of DSE | At the Audit Committee on the 15 November 2018 the Members were informed that "Information Asset Owners have been identified across the full breadth of activity and will be important to future assurance work." Examination of two Heads of Service Job Descriptions did not identify detail of the role and expectation of being an Information Asset Owner. Given the significance of this role it is recommended that job descriptions should specifically identify this important role and that the Heads of Service should acknowledge the requirements of being an Information Asset Owner Recommendation All Information Asset Owners to have within their job descriptions a clearly defined role in relation to information governance. (Priority 3) | 22/10/19 |  | Contact: Action Owner – Cristiana Emsley Cristiana.emsley@cleveland.pnn.police.uk 01642 302212 Delivery Manager – as above Report Published September 2019 Presented to Audit Committee Management Comment A Scheme of Delegation will be developed outlining the role of the IAO, this will be instead of a change in job description as the majority of IAO are police officers with no job role. This will be completed and delivered at the meeting on the 22nd Update October 2019 A Scheme of Delegation will be developed outlining the role of the IAO, this will be used instead of a change in job description as the majority of IAOs are police officers with no job role. |  |
| 356 | ES2019 | Chief Executive and Monitoring Officer | In reviewing key polices It was noted that the Reporting Professional Standards Concerns and Protected Disclosure Policy acted as the Force's Whistle Blowing Policy. The Police and Crime Commissioner also has a Whistle Blowing Policy titled "Public Interest Disclosure Policy" (last updated September 2014). If the PCC Whistle Blowing Policy only refers to the OPCC then this should be clearly stated and any reference to the Force removed to avoid any confusion. Recommendation The OPCC to review their Public Interest Disclosure Policy and if this only applies to the OPCC then this be clearly stated and reference to the Force removed. (Priority 3) | Complete |  | Contact: Action Owner – Simon Dennis OPCC Delivery Manager – as above Report Published September 2019 Presented to Audit Committee Management Comment The PCC’s Chief Executive & Monitoring Officer does not concur with the underlying suggestion in the recommendation to the effect that action should be taken to explicitly limit the remit of the policy the employees of the PCC. For several legal and regulatory reasons, the policy is accessible to all police personnel. The Chief Executive will review the policy and make amendments (and refresh other provisions in the policy) to make the position clear and to ensure that the policy is fully up to date. Update September 2019 The PCC has approved the refreshed policy and it will shortly be re-published on the PCC website and promoted on Message to All. Action complete |  |
| 357 | ES2019 | Head of Corporate Services | It was noted that although there is a web page for policies on the force's web site but there were no actual Policies listed. A key value of the Force is Transparency and as such non confidential policies should be available on the web. Recommendation The Force to append relevant policies onto the website to support its transparency value. (Priority 3) | 30/11/19 |  | Contact: Action Owner – Louise Solomon louise.solomon@cleveland.pnn.police.uk 01642 301311 Delivery Manager – as above Report Published September 2019 Presented to Audit Committee Management Comment As an interim measure the wording on the current Force website has been updated to reflect the fact that no policies are currently available. A workstream has been added to the Single Online Home Project to ensure that at the point of implementation of a new Force website the Force is compliant with FOI guidance in relation to the publication of non-confidential policies. Update September 2019 Policy owners have been contacted about their policies to identify any, not already marked ‘Official Sensitive’, that can’t be published in part or whole, before they are prepared for publication. Update October 2019 All policies, except those marked Official Sensitive, have been prepared for publication and will be available on the Single Online Home site when it goes live. Action Complete once site is live. |  |
| 358 | C2019 | ACCs for Nersou & CDSOU | While at the outset there is a business case to support any collaboration and it would identify efficiency, cost and/or effectiveness benefits as required under the Police Act, it has been difficult to establish / prove that once the collaboration is established that the original business case benefits have actually been realised. While the NERSOU and CDSOU collaborations have been ongoing for some time it would be good practice to review benefits as an ongoing exercise, say annually. An ongoing collaboration should demonstrate that benefits are sustained or continue to accrue to justify its continuing existence. Recommendation All collaboration projects to have an annual benefits realisation report to confirm that benefits are continuing to be achieved and where possible benefits be tangible. (Priority 2) | 31/3/2020 |  | Contact: CFO, ACO and ACCs Report Published October 2019 Presented to Audit Committee Management Comment Local projects will have benefits realisation reviews - CFO & ACO Regional reviews to be discussed at the governance groups to ascertain the ability to formulate annual reports - ACCs for NERSOU & CDSOU |  |

Reference key to Audit Reports:

| Reference | Report Title | Published | Presented to Audit Committee |
| --- | --- | --- | --- |
| C2019 | Collaborations | October 2019 |  |
| CG2019 | Commissioner’s Grants | July 2019 |  |
| DMS19 | Duty Management System | February 2019 | 28/2/19 |
| DQ2019 | Data Quality / Information Governance | September 2019 |  |
| ES2019 | Ethical Standards and Embedding Culture | September 2019 |  |
| FOI2018 | Freedom of Information 2018 | April 2018 | 24/5/18 |
| HRR19 | HR Recruitment 2019 | February 2019 | 28/2/19 |
| ICS2017 | ICT Cyber Security 2017 | September 2017 | 14/12/17 |
| ICTF2019 | ICT Firewall Security 2019 | April 2019 | 23/5/19 |
| ICTNS2019 | ICT Network Security 2019 | May 2019 | 23/5/19 |
| KFC2018 | Key Financial Controls 2018 | November 2018 | 28/2/19 |
| LW2018 | Lone Working 2018 | November 2018 | 28/2/19 |
| P2019 | Assurance of Payroll 2019 | February 2019 | 28/2/19 |
| SARC19 | OPCC contract for SARC and ISVA | February 2019 | 28/2/19 |
| SC2019 | Seized Cash 2019 | April 2019 | 23/5/19 |

|  | Complete; awaiting sign off by the auditors |
| --- | --- |
|  | Recommendation being progressed |
|  | Action against the recommendation to commence |

| Priority 1 | Urgent |
| --- | --- |
| Priority 2 | Important |
| Priority 3 | Routine |