Internal Audit Update Report for the Audit Committee June 2024

This document has been prepared for the Audit Committee to provide a status update in relation to the Force’s actions arising from Internal Audit Inspections.

The current ‘open session’ Force register includes 21 recommendations, with the oldest having been published in September 2023. The table below provides a ‘quick’ summary of the live actions:

| Report | High Priority | Medium Priority | Low Priority | Comment |
| --- | --- | --- | --- | --- |
| Sickness Absence 2023 |  | 2 (2) |  | All identified as complete – awaiting review by RSM |
| Training |  |  | 4 (4) | All identified as complete – awaiting review by RSM |
| Health and Safety 2023 | 2 (2) |  | 5 (5) | All identified as complete – awaiting review by RSM |
| Victims Code | 2 | 4 | 1 | All actions progressing |
| Ethical Standards |  |  | 1 (1) | Action and suggestion identified as complete – awaiting review by RSM |
| HR: Performance & Capability |  |  |  | Not yet finalised |
| ICT Security Controls |  |  |  | Not yet finalised |
| Total | 4 (2) | 6(2) | 11 (10) |  |

(*) numbers in brackets represent actions identified as complete by the Force, awaiting RSM Follow-up review.

Of the 21 ‘open session’ recommendations 14 have been identified, so far, as complete by the Force; as these have to be signed off by the auditors, they will remain on the action plan as “Closed locally awaiting sign off” until this is fulfilled.

The remaining live actions continue to be monitored, with regular updates provided by their owners.

The action plan below provides further details of the ‘live’ actions with status updates from the action owners.

It should be noted that the RAG (Red, Amber and Green) rating descriptors have been amended to reflect the completion status of the recommendation. The colour key and other details can be found at the end of the report.

Gill Currie

HMIC Liaison Officer

Cleveland Police

[Type the abstract of the document here. The abstract is typically a short summary of the contents of the document. Type the abstract of the document here. The abstract is typically a short summary of the contents of the document.]

| No. | Report | Action Owner | Management Action | Implementation Date |  | Action Progress | Delivery Group | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Original | Revised |  |  |  |
| 548 | Sickness Absence 2023 | Senior HR Business Partner | Management will review the current completion KPI for the attendance management training in August 2023, and a new KPI will be determined to capture as many people as possible and a new timescale will be agreed. (Medium) | 31 January 2024 | Complete | Report Published August 2023 Presented to Audit Committee 28th September 2023 Update September 2023 End August 2023 achieved completion rate of 51%. As at 13 Sep now 54% completion. New KPI Target 100% Line Managers to have cascade session completed before end Jan 2024 and work is underway to meet this target by end Jan 2024. Update October 2023 Completion rate as at 11 October 2023 61.3% work continues to work towards target for Jan 2024 Update November 2023 Completion rate 62.5% at end of October. Looking at digital means to complete rest of sessions and meet required levels of attendance. Update January 2023 Best options being investigated to deliver information digitally and will then look at plan to cascade to meet required level, Request to extend date to 30 June 2024 to allow digitisation of training and allow implementation for completion. Update March 2024 Digitisation of Training slides and recording of training is being completed early March. The cascade of the digital training will be sent to those who have not yet completed the training (including any new Sergeants) with the aim to cascade by end of March. This will then ask them to complete via digital means and be completed throughout April, May, and June to allow time for individuals to complete the digital training process. Further updates will be provided with completion rates once cascaded. Update April 2024 Due to technical challenges with the initial digital recording this has now been re-recorded via an alternative system. Anticipated that will be cascaded to individuals who have not yet attended training w/c22/4 for them to complete. The target audience is directly to those Line Managers that should attend but have not yet attended the training as well as new managers. The recording is ready, and managers will be asked to complete a form to confirm they had viewed which includes some additional questions based on the material. Update May 2024 Digital training was targeted to those that have not yet attended training. Individuals were sent an email w/c 22/4/2024 with a link to the Microsoft form and the learning to listen to; form to be completed post listening to the training. As of 7 May, current completion rate overall (includes the original face to face/teams and digital training) is 70% completion. This is monitored and will be updated as people complete the training. Update June 2024 Digital training has been cascaded to those that had not yet completed the in person training as well as new managers. Individuals completing the training are tracked via the online forms and the completion rate is increasing. As of 29 May 2024 the completion rate is 83.2% The team continue to chase individuals to complete the training, it was never expected to reach 100% due to sickness/maternity leave etc. The increase correlates to the efforts being made to get all the relevant staff trained and that will continue and be given to new staff as appropriate. This is a Low graded action and the Force has clearly shown a massive improvement, as such we are recommending the action for closure. An updated position can be obtained during the Follow-up audit. As of 10th June 2024 84.5% Action Complete | People and Wellbeing Board |  |
| 549 | Sickness Absence 2023 | Senior HR Business Partner | The People and Development Team will undertake quarterly dip sampling on all live sickness absence records to confirm they have retained all required documentation for the sickness period and to ensure management are appropriately updating Oracle in line with the agreed timescales documented in the procedural guidance. Results and trends from the dip sampling will be fed through the HR Business Partners to their associated Head of Service to allow them to take the appropriate action within their teams and departments. This will also be included in the data pack presented to the Head of Service on a quarterly basis so they can monitor staff discrepancies on the attendance management process. (Medium) | 31 January 2024 | Complete | Report Published August 2023 Presented to Audit Committee 28th September 2023 Update September 2023 Plan currently being created which will focus on activities and actions to help reduce overall sickness %. Plan anticipated to be completed by end October 2023. Update November 2023 Plan will be presented to the SWFPB by end of November 2023 with actions. Update December 2023 Dip sampling checks carried out Feb 2023 with error rate 17% then carried out further check 30/6/23 error rate reduced to 7%. Reported to SWFPB and action closed. See below action log as evidence closed action. POP plan created and being presented to SWFPB in Dec 2023. Update January 2024 POP plan in final stages of creation before final approval following discussions and feedback, over the past few months. Request to extend this to 31 March 2024 to allow approval and POP plan to start implementation. Update March 2024 Dip sampling is being carried out in March 2024 and data will be communicated to commands following the dip sampling activity. Update April 2024 Weekly Activity. HR process includes weekly checks carried out by ER team. Sickness records are checked weekly and discussed/highlighted to managers. Evidence: A copy of the weekly sickness spreadsheet to review current sickness (as of 8 April 2024) with examples of some emails (Redacted) sent on the back of the weekly sickness list. Update May 2024 Activity carried out in April to review March’s sickness data and complete dip sampling. From full list of sickness selected every 10th person to be checked giving a total of 31 people. Checks include Review of online Oracle system fit notes, occasions of welfare contact/types, date the sickness was closed down and when the RTW was completed. Evidence Copy of sickness dip sampling Summary shared with ER and HRBP Teams Slides taken from SLT packs which confirmed outcome of dip sampling completed in March. Action Complete | People and Wellbeing Board |  |
| 551 | HR Training 2023 | Head of Learning and Development | The Developing You, Learning and Development Policy or the Learning and Development Procedure will be updated to record the training that is mandatory for officers to complete and outline roles and responsibilities for managing in-person training between departments. Once the policy and procedure is approved, the documents will be made available and communicated to all officers. (Low) | 31 January 2024 | Complete | Report Published September 2023 Presented to Audit Committee xxx 2023 Update October 2023 Draft overarching policy being finalised ready to consult, during Nov/Dec 2023 with then request for approval following consultation. The policy will include a link to the L&D SharePoint site which records details of training that is mandatory. Further updates will be provided following consultation. Update December 2023 The draft policy will be sent for consultation Jan/Feb 2024 and once consultation completed will follow the approval process. Further updates to follow. Update January 2024 Policy has been through some pre consultation with L&D governance board, formal consultation will be required (is part of wider policy transformation for people and development). Formal force consultation is required along with approval from Executive management Board. Request to extend audit point to 30 June 2024. Update March 2024 Formal consultation requested in March (period of 4 weeks) once completed any comments/feedback will be considered and where appropriate any amendments made prior to gaining approval of documents. Update April 2024 Policy and Procedure is out for formal consultation runs until 17 April 2024. Once completed will review any feedback and make any necessary amendments, then will seek approval at the Executive Management Board (EMB). Planned to request approval on 3 May 2024 EMB. If approved will then arrange for upload and cascade to force. May Update 2024 The L&D policy and L&D Procedure were approved at the Executive Management Board on Friday 3rd May. Both have now been uploaded to the Force intranet and comms provided. Action Complete | People and Wellbeing Board |  |
| 552 | HR Training 2023 | Head of Learning and Development | The Force will ensure the decision and approval to mandate training will be recorded for example within the relevant action and decision log. This will be included as an agenda item at the Learning and Development Governance Meeting. (Low) | 31 October 2023 | Complete | Report Published September 2023 Presented to Audit Committee xxx 2023 Update October 2023 There have been no recent requests to mandate training since the June/July review, There has been a verbal request for mandated training which will be submitted to an L&D governance board. Once this has been reviewed copies of the agenda and the action and decision log will be provided. Update November 2023 No meeting held in November. The December meeting will consider any requests for mandatory learning and a copy of the decision and action log will be provided with the outcome. Update December 2023 Review of process for approval of mandated training currently underway. Further update will be provided in 2024. Update January 2024. The governance structure is under review and mandated training will be included and directed to the appropriate board. There have been no recent requests for internal mandated training since this audit action. Request to extend the action point to 29 February 2024. Update February 2024 Decision re mandating of a new or existing training module is part of the agenda for the L&D governance group. An example of the agenda is attached for March 2024. L&D governance meetings are held monthly, and any decisions will be added to the action and decision log to confirm any requests have been confirmed. Evidence Copy of Agenda showing mandatory training as an agenda item Action and Decision Action Complete | People and Wellbeing Board |  |
| 555 | HR Training 2023 | Learning and Development Manager | Revised Action February 2024 The Driver Training Manager will send subsequent reminders to line managers if drivers are not booked onto courses and the training has expired to remind officers not to drive vehicles with blue lights (and that officers are not carrying out blue light activity without the correct training). (Low) Original Action The Force will introduce a mechanism to monitor driver training compliance for officers so that officers and supervisors have access to accurate training expiry information so driving training refresher requirements are known. The Force will review the controls in place to prevent officers without an appropriate level of driver training being able to drive certain police vehicles, e.g. a vehicle with blue lights. (Medium) | 30 June 2024 | Complete | Report Published September 2023 Presented to Audit Committee xxx 2023 Update November 2023 Driver Training Manager will email to Line Managers to advise upcoming expiry of driver training. Managers will review their areas and individuals will book themselves onto the course. This activity is in addition to managers and individuals being able to see driver training expiry on the Oracle system. Evidence provided of email sent to Managers. (names redacted) Line Managers will be aware of their teams’ abilities and restrictions and when booked onto training. If driver training expires individuals will still be able to drive Police vehicles with their basic training and normal drivers’ licence but are unable to carry out blue light activity (go at excess speeds, chase suspects, drive through red lights etc.), they can only do this if they are within their relevant driver training. The activity that they will be able to do still allows them access to drive Police vehicles. Action Complete In the RSM follow up 2 February 2024, they identified this action as partially complete only. A revised action, level and delivery date were issued as per the action column. Update March 2024 Additional wording is being added to the email confirmations prior to the next review and batch of emails being sent which will accommodate the audit point. A blank copy of this email will be provided for the next update in April 2024. The next review and chase emails will be sent by the end April 2024 and any examples of officers emails will be provided as additional evidence once these emails have been sent. Update April 2024 A new email template has been created which is attached for evidence. This email will be sent out to line managers listing officers (if any) that are due to expire, next updates are due End April/start May though cannot guarantee any officers will fall into these criteria. Evidence – Copy of Email Template Action Complete | People and Wellbeing Board |  |
| 559 | HR Training 2023 | Head of Business Support | The Force will review the Oracle system to ensure non-attendance at training triggers an automated email to the relevant officer’s supervisor to inform them of non-attendance. (Low) | 30 April 2024 | Complete | Report Published September 2023 Presented to Audit Committee xxx 2023 Update November 2023 Work being undertaken to review the Oracle system further updates will be provided once this has been concluded. Update December 2023 Work still continuing to look at Oracle system further updates will be provided once complete. Update February 2024 Oracle resource identified to look at Oracle system and why some supervisors receive a notification, and some don’t. Currently going through vetting – no timelines identified. Update March 2024 The system produces an email to the individual and line manager to show that an individual has cancelled a course (this email is generated if the individual cancels or does not attend). To create separate emails for non attendance and cancellation would mean an additional cost to the force to change the system, when the outcome is the same i.e. the supervisor to discuss with the individual why they didn’t attend and to re-arrange if appropriate. Evidence The email is sent to the individual and the line manager, the below shows what these emails include: Notification to individual that training has been cancelled. Notification to Line Manager that training has been cancelled. Action Complete | People and Wellbeing Board |  |
| 571 | Health and Safety 2024 | Health and Safety Manager | Further guidance documentation will be created and made available to officers and staff to ensure they are given sufficient support to discharge their health and safety duties and responsibilities. In particular, the Force will develop a flowchart covering the process for reporting injuries on duty. (Low) | 30 April 2024 | Complete | Report Published February 2024 Presented to Audit Committee March 2024 Update November 2023 The existing flowchart(2016) has been updated and messages to all issued to the Force (evidence of both provided) forms and further information are available to staff on the Health and Safety>Injury on duty section of SharePoint. Action complete |  |  |
| 572 | Health and Safety 2024 | Health and Safety Manager | The sponsor in charge of the ‘Health and Safety in the Workplace’ training module will agree a frequency for training to be refreshed and communicate this to the Learning and Development Team to ensure this is reflected on the e-learning system. (Low) | 30 April 2024 |  | Report Published February 2024 Presented to Audit Committee March 2024 Update November 2023 Health and Safety training is required to be repeated every 3 years, evidence has been provided to show how this is set up on the system. The performance team replicate this requirement in the Power Bi dashboards. Email showing the set up on College Learn provided as evidence. Action Complete |  |  |
| 573 | Health and Safety 2024 | Health and Safety Manager | The Health and Safety Manager and chairperson will raise training non-compliance within the health and safety quarterly meetings to ensure management are aware of officers and staff are not completing training and that it is their responsibility to chase outstanding training to increase compliance. This could be undertaken via a standing agenda item at each meeting. (Low) | 30 April 2024 | Complete | Report Published February 2024 Presented to Audit Committee March 2024 Update November 2023 Frequent reminders are issued to all staff to complete the mandatory Health and Safety training (copy messages provided as evidence), the Power Bi screen shots show the increased uptake. The completion of mandatory training forms part of all personnel Performance Development Reviews. The Health and Safety meeting Decision and Action log evidences discussions regarding the completion of the mandatory training and actions issued to improve compliance. Action Complete |  |  |
| 574 | Health and Safety 2024 | Health and Safety Manager | The inspections that are overdue on the health and safety inspection programme will be completed. The drop-in buildings will be risk assessed with those that are used more often or where an existing inspection has not been completed prioritised. The Health and Safety Team will complete any required follow up inspections and prioritise any buildings deemed to be high risk. (High) | 31 July 2024 |  | Report Published February 2024 Presented to Audit Committee March 2024 Update November 2023 All building assessments are to continue on an annual basis. All assessments are complete for year 2023 and all drop in centres have also been visited. At this time there is no requirement to risk assess and prioritise as all inspections are up to date. The building assessment programme spread sheet has been updated to include ‘due by’ dates. The record is stored and maintained on the H&S SharePoint site. Assessments are continually being completed. Action complete |  |  |
| 575 | Health and Safety 2024 | Health and Safety Manager | The date of last inspection will be recorded on the inspection programme to ensure health and safety inspections and fire risk assessments are completed at least once per year. (Low) | 30 April 2024 | Complete | Report Published February 2024 Presented to Audit Committee March 2024 Update November 2023 The building assessment programme spread sheet has been updated to include ‘due by’ dates and the date of the last inspection. The record is stored and maintained on the H&S SharePoint site. (evidence provided) Action complete |  |  |
| 576 | Health and Safety 2024 | Health and Safety Manager | Supervisors will be reminded that they are required to complete a supervisor's reporting form when an officer is injured on duty. Officers and staff will be reminded to complete the injured person reporting form as soon as possible if they are injured. If this is not possible, supervisors should be completing the form on behalf of the officer to ensure a record is on file and the Health and Safety Manager can complete a RIDDOR report if appropriate. Both injured person reporting forms and supervisor's forms will be reviewed by the Health and Safety Manager and escalated to health and safety quarterly meetings if they are not submitted in a timely manner. This will ensure RIDDOR reporting can be completed within the set timescales. (High) | 31 March 2024 |  | Report Published February 2024 Presented to Audit Committee March 2024 Update November 2023 As per action 571, reminders have been issued to both staff and supervisors around the need to complete Injury on Duty (IOD) forms in a timely manner. A flowchart has been created for ease of use and IOD forms are accessible from the Health and Safety>Injury on duty section of SharePoint. (evidence provided) Additional messaging has been issued in relation to timescales around RIDDOR reporting. (evidence provided) The Health and Safety meeting Decision and Action log evidences IOD form reporting to the meeting and actions issued in relation to this. The Health and Safety Manager provides data to the quarterly meetings relating to IOD/RIDDOR via a report (copy provided as evidence). Action complete |  |  |
| 577 | Health and Safety 2024 | Health and Safety Manager | Terms of reference for the quarterly health and safety meetings will be created and approved by an appropriate body. (Low) | 30 April 2024 | Complete | Report Published February 2024 Presented to Audit Committee March 2024 Update February 2024 Terms of Reference relating specifically to the quarterly Force Health and Safety meeting were drafted and presented to the February meeting. These were approved. Evidence provided. Action Complete |  |  |
| 578 | Victims Code 2024 | Force Victims Lead | The Force Victims Lead will work with the developers of Niche to understand how the victim of crime booklet section can be bypassed and how this can be rectified. Once this issue has been addressed, the Force will continue to monitor this through the monthly audit inspections and ensure the fields are mandatory. (Medium) | 31 July 2024 |  | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 It is believed that the section can only be bypassed by manually "crashing" NICHE. This is evidenced in other compliance areas such as recording ethnicity. The Victim and Witness contact module cannot be updated by individual forces and a change to it would have to be a national changes. There has been a request for a national change, however, the ongoing work around the digital case file has superseded this. The request for updates to the VWCM is to be raised at the Minerva group, request provided as evidence. | Victim and Witness Group |  |
| 579 | Victims Code 2024 | Force Victims Lead | The Force will ensure that the victims' code module on Niche is completed for all crimes with a victim. This will be supported through a variety of measures: - the Power Bi dashboard and Inspectors' audits will continue to be used to identify instances where an officer is not completing the victims' code module. - any exceptions will be discussed with the relevant officer or staff member to ensure they are aware of their responsibilities. - any themes or trends identified will be raised and discussed with the Victim and Witness Group. This includes identifying specific teams that are less likely to be completing the victims' code module; and - the Force will hold a series of training days to appropriately educate officers and staff. Whilst this will not exclusively cover the victims' code module, it will be included. (High) | 31 May 2024 | 31 July 2024 | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 The current compliance rate for inclusion of the Victim Code Module is 94%. This is a high level of compliance. The activity outlined in the management action is progressing: - Power BI dashboard for Victim’s module features in force IMPACT and Response policing performance indicators. The Inspectors audit continue to review the presence and quality of the Victim module and provide feedback to operational teams in relation to it. - Specific themes are discussed in the V&W meeting, albeit, performance is at an improved level. Delivery of training to all operational Sgts has commenced, this includes guidance in relation to the victim contact module. In the coming months a bitesized video will be formulated in relation to victim care, included the same. | Victim and Witness Group |  |
| 580 | Victims Code 2024 | Force Victims Lead | The Force Victims Lead will work with the Force's Corporate Communications Department to agree a series of internal communications to remind officers and staff of their requirement with regards to the Victims' Code. This will include: - the requirement to fully complete the victims' code module on Niche; - that the victims’ code module should be completed when an officer is the victim; - the victim being contacted at the agreed contact frequency; and - victims being contacted at the relevant trigger points. (High) | 31 May 2024 | 31 July 2024 | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 Through benchmarking the following pneumonic has been proposed to assist: V; Victim needs assessment. O; Officer contact details and crime number. I; Information leaflet – QR code. C; Contact agreement – agree frequency and means of updates. E; Explanation – what will happen next, what they should expect and outcome of investigation. VIPS – for victim needs assessment Action is progressing regarding the implementation of this with Corporate Comms. | Victim and Witness Group |  |
| 581 | Victims Code 2024 | Force Victims Lead | The Force will ensure all officers are recording a proportional contact frequency with victims and that this is adhered to. Where officers are not able to contact the victim at the required frequency, appropriate rationale will be documented to explain this. As well as contacting victims at the agreed frequency, officers will also ensure contact is made at each of the agreed trigger points (such as arrest and charge). This action will be supported by the measures identified in management action two and three (579, 580). (Medium) | 31 May 2024 | 31 July 2024 | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 The inspectors audit asks a question in relation to the length of time between updates “Is this a reasonable length of time?” 72% of respondents say that it is a reasonable length of time. Of the 28% that don’t, it appears a proportion of these relate to cases were the victim is not in support and so the OIC has included 999d in the update field. | Victim and Witness Group |  |
| 582 | Victims Code 2024 | Force Victims Lead | The Force will work with the developers of Niche to identify any potential opportunities for recording data regarding the victim personal statement. In particular, this will be reviewed alongside the upcoming KPIs to ensure any options are in line with proposed performance metrics. (Low) | 31 July 2024 |  | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 NICHE digital statement has pre-defined questions around whether a VPS has been offered and taken. The data can be extracted from NICHE. The Performance Team are in the process of extracting this data and adding it to the Victim and Witness performance suite. | Victim and Witness Group |  |
| 583 | Victims Code 2024 | Supervisor - Witness Care and Central Ticket Office | The Witness Care Unit will ensure victims are contacted in a timely manner after each of the relevant stages within the court process. This will include consideration for victims that may require enhanced needs. As well as this, the new monitoring form will be introduced to better track performance metrics and ensure the correct details are recorded. (Medium) | 31 May 2024 | 31 July 2024 | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 Head of CJ has agreed an audit regime and created a monitoring form for recording the reviews, results will be monitored over the coming months. | Victim and Witness Group |  |
| 584 | Victims Code 2024 | Force Victims Lead | The Force will ensure that victim needs assessments are completed and that this is done so in a timely manner. Officers will also be reminded of the importance of identifying whether the victim is entitled to enhanced needs and ensuring an initial update is provided within 24 hours. This action will be supported by the measures identified in management actions two and three (579,580). (Medium) | 31 May 2024 | 31 July 2024 | Report Published January 2024 Presented to Audit Committee March 2024 Update May 2024 NICHE records the presence of the outcome of the Victim needs assessment in the Victim Contact Module. This data can be exported from NICHE and used for performance management and compliance purposes. The Performance Tean are working to export the data at present it into a suite of Victim performance metrics. The working behind how the Victim needs assessment results was arrived at is not recorded. This is an identified gap locally and nationally. The College of Policing and NPCC are formulating (by Dec 2024) guidance on what a Victim needs assessment needs to consider. In the interim, DI Specialist Crime has formulated a tasking and finish group to liaise with victim care agencies and other key stakeholders to formulate a Cleveland VNA. | Victim and Witness Group |  |
| 585 | Ethical Standards 2024 | Operational Ethics Lead | Once the new Code of Ethics is rolled out, mandatory training will be created and made available to staff to ensure they are aware of the new changes. Compliance will be monitored and any instances of staff not completing training will be escalated as per the Force's training process. (Low) | 31 October 2024 | Complete | Report Published February 2024 Presented to Audit Committee March 2024 Update May 2024 The College of Policing have provided 7 modules and the force has made this mandatory for all, confirmed in April 2024 via the Learning and Development Board, supported by the Ethics and Standards Board. This training will also be completed by any person joining the force so will be something all have completed. The training is largely e-learning and monitored by Power BI which will show completing rates for individuals, teams, commands, and departments. One Module (4) is an in-person module, so will require all staff to be trained in small groups. As such, for 100% delivery to be achieved it is likely to take the remainder of the year. Action complete. Evidence provided to show the training has been identified as mandatory. Power BI Page for monitoring completion | Ethics and Standards Governance Group |  |
| 586 | Ethical Standards 2024 | Operational Ethics Lead | Suggestion: The Force will consider the drawbacks and benefits of using a formal criteria framework to assess ethical dilemmas. | 31 October 2024 | Complete | Report Published February 2024 Presented to Audit Committee March 2024 Update May 2024 A formal criteria framework is now business as usual for the assessment of ethical dilemmas, agreed in the Ethics and Standards Board and documented in the Action and Decision Log. This will formalise a list of assessment criteria, including Code of Ethics, policies, Standards of Professional Behaviour, and Legislation, whereas previously this was more ad hoc and relied on the writer and board / committee considering them. For thoroughness, the various aspects included were generally captured previously, but this formalises the list for consideration so will not be missed in future. Complete | Ethics and Standards Governance Group |  |

Reference key to Audit Reports:

| Colour Code for actions – final column |  |
| --- | --- |
|  | Complete; awaiting sign off by the auditors |
|  | Recommendation being progressed |
|  | New Action – first update not yet requested/received |
|  | Action against the recommendation to commence |

| Report Title | Grading | Published | Presented to Audit Committee |
| --- | --- | --- | --- |
| Ethical Standards | Substantial Assurance | February 2024 | 28/3/2024 |
| Health and Safety 2024 | Partial Assurance | February 2024 | 28/3/2024 |
| HR Training | Partial Assurance | September 2023 | 12/12/2023 |
| Sickness Absence 2023 | Reasonable Assurance | August 2023 | 28/9/2023 |
| Victims Code | Partial Assurance | January 2024 | 28/3/2024 |